## Backlog
ID | Epic | Epic name | Story | Persona | Tier | Priority | Size | Depends on | Acceptance criteria | Status | Owner
E00-01 | E00 | Platform and data foundation | Accounts with a patient-owned health graph and linked family accounts; in-region hosting (SG or MY) | System | T1 | P1 | L |  | Patient node owns all data; family accounts attach via grants; data at rest in region | Backlog
E00-02 | E00 | Platform and data foundation | Consent capture at onboarding: explicit, revocable, versioned, exportable as a PDPA record | All | T1 | P1 | M |  | Consent event stored with timestamp, scope and version; revocation removes access within a minute | Backlog
E00-03 | E00 | Platform and data foundation | Memory stores: episodic (raw artefacts), semantic (facts), working (current episode) with provenance on every fact | System | T1 | P1 | L |  | Every semantic fact links to at least one artefact and a confidence | Backlog
E00-04 | E00 | Platform and data foundation | State model service recomputing clinical, functional, cognitive, situational, preference and family state | System | T1 | P1 | L | E00-03 | State recomputes on any new fact; every card records the State it was rendered from | Backlog
E00-05 | E00 | Platform and data foundation | Trigger engine implementing rule, pattern and event triggers with per-type channel and daily caps | System | T1 | P1 | M | E00-04 | No persona receives more than the configured cap per day; every trigger logs its rule | Backlog
E00-06 | E00 | Platform and data foundation | Licensed drug database and interaction API integration (local registries MY NPRA, SG HSA) | System | T1 | P1 | M |  | Brand to generic resolution for a sample of 200 MY/SG products above 95% | Backlog
E00-07 | E00 | Platform and data foundation | Audit log service for every read, write and share | System | T1 | P1 | S |  | Any access to patient data is queryable by patient and chief | Backlog
E00-08 | E00 | Platform and data foundation | Offline cache for today's medicine list and emergency card; runs on five-year-old Android at 360px | Dad | T1 | P1 | M |  | Cold start under 3s on a reference low-end device; card readable with no data | Backlog
E00-09 | E00 | Platform and data foundation | Export (PDF, FHIR bundle) and full deletion | All | T2 | P2 | M | E00-03 | Export completes under 60s; deletion removes all stores and confirms | Backlog
E01-01 | E01 | Onboarding and health biography | Chief-led onboarding: who the patient is, who the family is, roles and language | Chief | T1 | P1 | M | E00-02 | Complete in under 10 minutes with no typed fields beyond names | Backlog
E01-02 | E01 | Onboarding and health biography | Health biography session: guided capture of existing papers into the record with agent assistance | Chief | T1 | P1 | L | E02-01,E02-02 | A shoebox of 30 documents becomes a reconciled record in one sitting | Backlog
E01-03 | E01 | Onboarding and health biography | Patient profile: conditions, language, functional and cognitive settings | Chief | T1 | P1 | S | E01-01 | Settings drive density mode and voice language immediately | Backlog
E01-04 | E01 | Onboarding and health biography | First-week activation plan: what to snap next, one prompt per day | Chief | T1 | P2 | S | E01-02 | Prompts stop once the record has medicines, last visit and next visit | Backlog
E02-01 | E02 | Capture and ingestion | Photo to OCR to structured extraction for labs, reports, prescriptions and receipts | Chief | T1 | P1 | L | E00-03 | Lab values extracted with unit and date at 95% on a labelled MY/SG test set | Backlog
E02-02 | E02 | Capture and ingestion | Handwriting recognition for clinic slips and handwritten prescriptions | Chief | T1 | P1 | L | E02-01 | Drug, dose and frequency read from handwritten slips with confidence shown | Backlog
E02-03 | E02 | Capture and ingestion | PDF import from portals, email and shares | Chief | T1 | P1 | S | E02-01 | Multi-page PDFs parsed into events with dates | Backlog
E02-04 | E02 | Capture and ingestion | WhatsApp inbound ingestion: forward a photo or PDF to the app number and it files itself | All | T1 | P1 | M | E02-01,E11-01 | Forwarded item appears in the record with a confirmation reply within a minute | Backlog
E02-05 | E02 | Capture and ingestion | Consult recording with consent prompt, transcription, speaker separation and timestamps | Chief | T1 | P1 | L | E00-02 | Consent captured before recording; transcript searchable; clip playable at a timestamp | Backlog
E02-06 | E02 | Capture and ingestion | Scribble and voice notes attached to any event | All | T1 | P2 | S | E03-02 | Note attaches to the selected event and appears in recall | Backlog
E02-07 | E02 | Capture and ingestion | Capture review card with per-field confidence and one confirm tap | Chief | T1 | P1 | M | E02-01 | Fields below threshold shown dotted; a single tap saves | Backlog
E02-08 | E02 | Capture and ingestion | Reading capture by photo of a device screen (BP cuff, glucometer, scale) | Dad | T1 | P1 | M | E02-01 | Value, unit and time captured from the screen photo; no typing | Backlog
E02-09 | E02 | Capture and ingestion | Pill and box photo to drug identification | Chief | T2 | P2 | M | E00-06 | Identifies registered MY/SG products by pack and registration number | Backlog
E02-10 | E02 | Capture and ingestion | Pharmacy receipt to medicine and cost | Chief | T2 | P2 | S | E02-01,E07-04 | Price and quantity feed the ledger and the running count | Backlog
E02-11 | E02 | Capture and ingestion | Wearable and home-device sync (Apple Health, Health Connect, BP cuff, glucometer, scale) | Dad | T2 | P2 | L | E00-03 | Readings arrive as events with source and device | Backlog
E03-01 | E03 | Memory and timeline | Appointments as the timeline spine: last check-up, last visit, next visit | All | T1 | P1 | M | E00-03 | Every artefact can attach to an appointment; radar shows all three anchors | Backlog
E03-02 | E03 | Memory and timeline | Episodes and events with artefacts hanging off them | Chief | T1 | P1 | M | E00-03 | An episode groups events across visits; timeline filters by episode | Backlog
E03-03 | E03 | Memory and timeline | Providers directory with history and chief notes | Chief | T1 | P1 | S | E03-01 | Every visit links to a provider; notes visible to chief only | Backlog
E03-04 | E03 | Memory and timeline | What changed diff view since the chief last looked | Chief | T1 | P1 | M | E00-04 | Lists new facts, unconfirmed doses and family notes since last open | Backlog
E03-05 | E03 | Memory and timeline | Natural-language recall: voice for Dad, text for chief, with citations and clip playback | All | T1 | P1 | L | E00-03,E02-05 | Answers cite the artefact; consult answers play the clip at the timestamp | Backlog
E03-06 | E03 | Memory and timeline | Body-systems tagging and map filter | All | T2 | P2 | M | E15-06 | Every insight carries at least one system tag; map filters timeline and feed | Backlog
E03-07 | E03 | Memory and timeline | Search across artefacts and transcripts | Chief | T2 | P3 | S | E03-05 | Full-text search returns artefacts with dates | Backlog
E04-01 | E04 | Medications | Reconciled medication list with source and confidence per line | Chief | T1 | P1 | M | E02-01,E00-06 | Each line shows which label or visit it came from; duplicates flagged | Backlog
E04-02 | E04 | Medications | Dose schedule anchored to routine with Taken taps for Dad | Dad | T1 | P1 | M | E10-01 | Doses render as paper cards at breakfast, dinner, bed; tap records time | Backlog
E04-03 | E04 | Medications | Interaction check on add, including supplements and TCM | System | T1 | P1 | M | E00-06 | New line screened before save; severity and the two drugs named | Backlog
E04-04 | E04 | Medications | Running count and reorder date from dispensed quantity, confirmed doses and lead time | System | T1 | P1 | M | E04-02 | Count updates per tap; reorder date shifts with lead time per source | Backlog
E04-05 | E04 | Medications | Reorder card with Ask-to-order and I-have-more actions | Dad | T1 | P1 | S | E04-04 | Card appears at threshold; Ask-to-order notifies the roster | Backlog
E04-06 | E04 | Medications | Medication story per drug: purpose in his words, how to take, watch-outs, avoid, if missed | All | T1 | P1 | M | E00-06 | Story rendered in Dad's language as a card and a voice note | Backlog
E04-07 | E04 | Medications | Missed-dose guidance per drug | Dad | T1 | P2 | S | E04-06 | Guidance from licensed monograph shown when a dose is late | Backlog
E04-08 | E04 | Medications | Polypharmacy review against Beers and STOPP/START surfaced as talking points | Chief | T2 | P1 | L | E04-01 | Runs at five or more medicines; each point cites the criterion; never instructs to stop | Backlog
E04-09 | E04 | Medications | Recount from a blister-strip photo | Dad | T2 | P2 | M | E02-01 | Count replaces estimate; requested only below seven days or sparse confirmations | Backlog
E04-10 | E04 | Medications | Helper given-taps on WhatsApp | Helper | T2 | P1 | S | E11-01,E12-05 | Helper reply records the dose as given by helper | Backlog
E04-11 | E04 | Medications | Dose change proposals from consult recording, confirmed by chief | Chief | T2 | P2 | M | E02-05 | Verbal change becomes a proposal card; label at next refill closes it | Backlog
E04-12 | E04 | Medications | Refill queue with drafted pharmacy or clinic messages | Chief | T2 | P2 | S | E04-04 | Everything due in 14 days listed; one tap drafts the message | Backlog
E04-13 | E04 | Medications | Fasting and festive schedule shifts | Dad | T2 | P2 | S | E04-02 | Schedule shifts where the drug allows; chief flagged where it does not | Backlog
E04-14 | E04 | Medications | Side-effect diary linked to medication changes | Dad | T2 | P3 | S | E14-01 | Symptoms logged near a change are linked to it | Backlog
E04-15 | E04 | Medications | Generic substitution and price comparison across pharmacies | Chief | T3 | P3 | M | E02-09 | Shows generic option and last known prices | Backlog
E04-16 | E04 | Medications | Old-stock handling for two strengths of one drug | System | T2 | P3 | S | E04-01 | Label decides current; other marked old stock | Backlog
E05-01 | E05 | Visit loop | Pre-visit brief: purpose, what changed, open questions, what to bring | Chief | T1 | P1 | M | E03-04 | Generated at T-3 days; editable; one page | Backlog
E05-02 | E05 | Visit loop | Questions to ask generated from gaps, memos and State; editable; one card for Dad | All | T1 | P1 | M | E05-01 | Questions carry their source; Dad's card is one screen | Backlog
E05-03 | E05 | Visit loop | Logistics card: time, place, parking, who is driving, what to bring | Dad | T1 | P1 | S | E12-03 | Driver pulled from roster; card sent T-1 and T-0 | Backlog
E05-04 | E05 | Visit loop | In-visit recording flow | Chief | T1 | P1 | S | E02-05 | One tap to start with consent prompt; ends into post-visit | Backlog
E05-05 | E05 | Visit loop | Post-visit summary in Dad's language with actions, medication changes and follow-ups | All | T1 | P1 | L | E02-05,E04-01 | Summary within 10 minutes of visit end; changes go to proposals; follow-ups scheduled | Backlog
E05-06 | E05 | Visit loop | Memo card at the end of every conversation | All | T1 | P1 | M | E00-03 | Decisions and commitments in the person's words filed to the next appointment | Backlog
E05-07 | E05 | Visit loop | Coverage and GL check before the visit | Chief | T2 | P1 | M | E07-01,E07-02 | Panel status, likely out-of-pocket and GL state shown on the brief | Backlog
E05-08 | E05 | Visit loop | Doctor-facing share link: expiring one-page brief, no login | Clinic | T2 | P1 | M | E05-01 | Link opens in a browser, expires in 72 hours, shows conditions, medicines, readings, questions | Backlog
E05-09 | E05 | Visit loop | Second-opinion packet export | Clinic | T2 | P2 | M | E03-02 | Bundle with summary, medicines, key labs, imaging list, prior opinions; readable in three minutes | Backlog
E05-10 | E05 | Visit loop | Visit prep workspace for the chief | Chief | T2 | P2 | M | E05-01 | Brief, questions, packet, logistics and GL in one screen | Backlog
E06-01 | E06 | Discharge and transitions | Discharge summary ingestion to plan with old-versus-new medicine reconciliation | Chief | T2 | P1 | L | E02-01,E04-01 | New medicines reconciled; red flags listed in plain language | Backlog
E06-02 | E06 | Discharge and transitions | Follow-up appointments extracted and scheduled | Chief | T2 | P1 | S | E06-01,E03-01 | Appointments appear on the spine with prep | Backlog
E06-03 | E06 | Discharge and transitions | 30-day readmission watch: daily check-in card, weight and symptom triggers, escalation | All | T2 | P1 | L | E00-05 | Escalation to the person on duty on trigger; watch ends at day 30 | Backlog
E06-04 | E06 | Discharge and transitions | Hospital bag and admission-day card | Dad | T2 | P2 | S | E07-02 | Card lists GL, ID, medicines, contacts | Backlog
E06-05 | E06 | Discharge and transitions | GP transition memo after discharge | Clinic | T3 | P3 | S | E05-08 | One page shared with the GP by link | Backlog
E07-01 | E07 | Insurance, cost and admin | Policy on file in plain language: insurer, plan, panel, limits, exclusions, renewal | Chief | T2 | P1 | M | E02-03 | Policy PDF parsed into plain-language fields with source pages | Backlog
E07-02 | E07 | Insurance, cost and admin | Guarantee-letter tracking with chasing messages | Chief | T2 | P1 | M | E07-01 | States requested, approved, rejected, expired; drafted chase message | Backlog
E07-03 | E07 | Insurance, cost and admin | Claims tracking with receipts attached | Chief | T2 | P1 | M | E07-01 | States submitted, pending, paid, shortfall | Backlog
E07-04 | E07 | Insurance, cost and admin | Cost ledger per episode and per year with SG and MY schemes | Chief | T2 | P2 | M | E02-09,E07-03 | Out-of-pocket, claimed and reimbursed totals by episode | Backlog
E07-05 | E07 | Insurance, cost and admin | Panel doctor list matched to conditions | Chief | T2 | P2 | S | E07-01,E03-03 | Panel providers filtered by sub-specialty | Backlog
E07-06 | E07 | Insurance, cost and admin | Cost expectation before care | Chief | T3 | P2 | L | E07-01 | Likely bill range for a visit, test or procedure at a named hospital | Backlog
E08-01 | E08 | Care navigation | Provider recommendation with reasons | Chief | T3 | P1 | L | E03-03,E07-05 | Ranked list with sub-specialty, history, panel, distance, timing and driver reasons | Backlog
E08-02 | E08 | Care navigation | Second-opinion logic | Chief | T3 | P2 | M | E08-01 | Different institution, matched sub-specialty, not the same practice group | Backlog
E08-03 | E08 | Care navigation | Best time and easiest route | Chief | T3 | P2 | M | E08-01 | Peak hours, travel time and parking shown per option | Backlog
E08-04 | E08 | Care navigation | Drafted WhatsApp or call script to the clinic; confirm before booking | Chief | T3 | P1 | M | E08-01 | No booking without an explicit confirm | Backlog
E08-05 | E08 | Care navigation | Transport coordination with the roster | Chief | T3 | P3 | S | E12-03 | Driver assigned from roster; card to Dad | Backlog
E09-01 | E09 | Intelligence and correlation | Lab trends with age- and lab-adjusted reference ranges | All | T1 | P1 | M | E02-01 | Trend per analyte with range band and direction in words | Backlog
E09-02 | E09 | Intelligence and correlation | Cross-signal correlation engine: readings, medicines, meals, sleep, symptoms | System | T2 | P1 | L | E00-03,E02-11 | Correlations computed with provenance; none shown below confidence threshold | Backlog
E09-03 | E09 | Intelligence and correlation | Pattern flags with provenance and confidence, phrased for a clinician conversation | All | T2 | P1 | L | E09-02,E16-01 | Every flag cites sources and ends with what to raise with the doctor | Backlog
E09-04 | E09 | Intelligence and correlation | Food snap to personal verdict with body-system tags | Dad | T2 | P2 | L | E00-04 | Verdict leads with what matters for his conditions; no calorie lecture | Backlog
E09-05 | E09 | Intelligence and correlation | Screening and vaccination schedule localised to MOH Malaysia and HealthHub Singapore | All | T2 | P2 | M | E01-03 | Due items appear on the feed and next visit questions | Backlog
E09-06 | E09 | Intelligence and correlation | Condition explainer clip in his language | Dad | T2 | P2 | M | E11-09 | 30-second clip with captions per active condition | Backlog
E09-07 | E09 | Intelligence and correlation | Seasonal and environmental alerts relevant to his conditions | Dad | T3 | P3 | S | E00-05 | Haze, dengue and heat alerts only when a condition makes them relevant | Backlog
E10-01 | E10 | Daily living and routines | Routine builder rendered per persona | Chief | T1 | P1 | M | E00-04 | Medicines, readings, walks, meals, sleep set once; renders to Dad and helper | Backlog
E10-02 | E10 | Daily living and routines | Meal guidance with hawker library and festive periods | Dad | T2 | P2 | L | E09-04 | Guidance by condition and culture; festive modes | Backlog
E10-03 | E10 | Daily living and routines | Mobility exercise clips and falls-risk check | Dad | T3 | P2 | M | E11-09 | Clips with captions; home-hazard checklist for the chief | Backlog
E10-04 | E10 | Daily living and routines | Sleep and hydration nudges only when relevant | Dad | T3 | P3 | S | E00-05 | Nudges gated by State | Backlog
E11-01 | E11 | Delivery, feed and WhatsApp | WhatsApp surface: cards, voice notes, Taken replies, family thread, inbound | All | T1 | P1 | L | E00-05 | Dad can complete a full day without opening the app | Backlog
E11-02 | E11 | Delivery, feed and WhatsApp | Ranked feed with today top three and why-am-I-seeing-this | All | T1 | P1 | L | E00-04 | Top three ordered alert, reminder, insight; every card explains itself | Backlog
E11-03 | E11 | Delivery, feed and WhatsApp | Card grammar components: one number, one direction, one colour, one action | All | T1 | P1 | M | E15-01 | Components enforce a single action per card | Backlog
E11-04 | E11 | Delivery, feed and WhatsApp | Voice notes generated from any card in Malay, Mandarin, English | Dad | T1 | P1 | M | E15-05 | Voice note under 30 seconds; Hokkien and Tamil at T2 | Backlog
E11-05 | E11 | Delivery, feed and WhatsApp | Trigger channels and caps per type | System | T1 | P1 | M | E00-05 | Reminder, alert and context cards route to the configured channel | Backlog
E11-06 | E11 | Delivery, feed and WhatsApp | Escalation ladder: Dad, helper, caregiver on duty, chief | System | T1 | P1 | M | E12-03 | Third nudge goes to roster, not Dad | Backlog
E11-07 | E11 | Delivery, feed and WhatsApp | Memo-based nudges in the person's own words | Dad | T1 | P2 | S | E05-06 | Nudges quote the memo; no system targets | Backlog
E11-08 | E11 | Delivery, feed and WhatsApp | Engagement feedback: format adapts to what he opens | System | T2 | P2 | M | E11-02 | Switches text to voice or clip to card after configured misses | Backlog
E11-09 | E11 | Delivery, feed and WhatsApp | 30-second clips: weekly recap, explainers, post-visit | Dad | T3 | P2 | L | E15-07 | Narrated in his language with captions; forwardable on WhatsApp | Backlog
E11-10 | E11 | Delivery, feed and WhatsApp | Morning card ritual at a fixed time tied to breakfast | Dad | T1 | P1 | S | E11-02 | One card daily; voice note twin | Backlog
E12-01 | E12 | Family, sharing and helper | Roles and scoped grants by category and time window | Chief | T1 | P1 | L | E00-02 | Chief, caregiver, viewer, helper, emergency-only; scope enforced on every read | Backlog
E12-02 | E12 | Family, sharing and helper | Family thread with digests, mixing health cards and messages | All | T1 | P1 | M | E11-01 | Digest per day per caregiver; no stream | Backlog
E12-03 | E12 | Family, sharing and helper | Duty roster and task assignment | Chief | T1 | P2 | M | E12-01 | Tasks assignable to siblings and helper; roster drives escalation and logistics | Backlog
E12-04 | E12 | Family, sharing and helper | Audit trail visible to Dad with only-me marking | Dad | T1 | P1 | M | E00-07 | Dad sees who looked at what; only-me hides from all grants | Backlog
E12-05 | E12 | Family, sharing and helper | Helper mode on WhatsApp in her language | Helper | T2 | P1 | M | E11-01 | Today's list with pill photos; given replies; not-well quick reply; no history | Backlog
E12-06 | E12 | Family, sharing and helper | Push composer with preview and scheduling | Chief | T1 | P1 | M | E11-04 | Chief sees exactly what Dad will see; sends at a State-appropriate time | Backlog
E12-07 | E12 | Family, sharing and helper | Caregiver load view: hours, tasks, distribution | Chief | T3 | P3 | S | E12-03 | Weekly view per family member | Backlog
E12-08 | E12 | Family, sharing and helper | Incapacity and death handling: who inherits the graph, what is deleted | Chief | T3 | P2 | M | E12-01 | Documented flow executed on a verified event | Backlog
E12-09 | E12 | Family, sharing and helper | LPA and consent document storage | Chief | T1 | P2 | S | E00-02 | Documents attached to the grant record | Backlog
E13-01 | E13 | Safety and emergency | Offline emergency card, lock-screen widget, printable page | Dad | T1 | P1 | M | E00-08 | Conditions, medicines, allergies, blood type, contacts, insurer in two languages; works with no data | Backlog
E13-02 | E13 | Safety and emergency | Not-feeling-well flow: voice capture, State check, what to do now, notify family | Dad | T1 | P1 | L | E00-04,E11-06 | Three steps; guidance is rest, call clinic or go now; family notified | Backlog
E13-03 | E13 | Safety and emergency | A&E versus clinic guidance with nearest appropriate option and cost | Dad | T3 | P2 | M | E13-02,E08-01 | Nearest option with expected cost | Backlog
E13-04 | E13 | Safety and emergency | Advance care planning documents stored and shareable | Chief | T3 | P3 | S | E12-09 | Documents shareable by link to the clinic | Backlog
E14-01 | E14 | Symptoms and observations | Symptom log by voice with severity and duration | Dad | T1 | P1 | M | E02-06 | Logged in his words; appears in the pre-visit brief | Backlog
E14-02 | E14 | Symptoms and observations | Photo timelines for wounds, rashes and swelling with side-by-side comparison | Dad | T2 | P2 | M | E02-01 | Two photos compared with dates | Backlog
E14-03 | E14 | Symptoms and observations | Mood and energy one-tap only when a condition or medicine makes it relevant | Dad | T3 | P3 | S | E00-04 | Gated by State; never framed clinically | Backlog
E15-01 | E15 | Design system and accessibility | Design tokens, state washes, glass and paper components | System | T1 | P1 | M |  | Tokens match design-system.md; washes cross-fade on State change | Backlog
E15-02 | E15 | Design system and accessibility | Dad density mode: 20px body, 56px targets, paper-first, one action per tile | Dad | T1 | P1 | M | E15-01 | Contrast 7:1 on every decision element | Backlog
E15-03 | E15 | Design system and accessibility | Chief density mode: glass-first, 16px body | Chief | T1 | P1 | M | E15-01 | Dense screens remain readable at 360px | Backlog
E15-04 | E15 | Design system and accessibility | Accessibility audit: contrast, dynamic type to 200%, reduced motion | All | T1 | P1 | S | E15-02 | Audit passes before T1 release | Backlog
E15-05 | E15 | Design system and accessibility | Localisation framework: Malay, Mandarin, English text; Tamil and Hokkien voice | All | T1 | P1 | M |  | Every string externalised; voice language per person | Backlog
E15-06 | E15 | Design system and accessibility | Body-systems map component | All | T2 | P2 | M | E15-01 | Outline figure with soft glows; doubles as filter | Backlog
E15-07 | E15 | Design system and accessibility | Clip and voice-note player | Dad | T1 | P2 | S | E15-01 | Large play target; transcript in Dad body size | Backlog
E16-01 | E16 | Trust, boundary and regulatory | Boundary copy on every inferring screen | All | T1 | P1 | S | E15-01 | Organises, prepares, surfaces patterns to discuss; does not diagnose or treat | Backlog
E16-02 | E16 | Trust, boundary and regulatory | Recording consent pattern with legal review in SG and MY | All | T1 | P1 | S | E02-05 | Doctor notified aloud or by printed notice; consent stored | Backlog
E16-03 | E16 | Trust, boundary and regulatory | SaMD boundary review (HSA, MDA): guideline-referenced, non-real-time, informational outputs | System | T1 | P1 | M | E09-03 | Written review signed off before any flag ships | Backlog
E16-04 | E16 | Trust, boundary and regulatory | High-risk drug rule: label photo required before a dose is saved | System | T1 | P1 | S | E04-01 | Warfarin, insulin, digoxin, methotrexate, opioids cannot be saved from voice alone | Backlog
E16-05 | E16 | Trust, boundary and regulatory | PDPA data map, breach process and DPO | System | T1 | P1 | M | E00-01 | Data map covers both countries; breach runbook tested | Backlog
E17-01 | E17 | Feeling cloud and smart nudges | State-conditioned feeling cloud on Today: base words plus emphasis and additions from State; shown only after a change, at most once a day | Patient | T1 | P1 | M | E00-04 | Words re-rank within a second of a State change; disappears after a tap or Fine today | Backlog
E17-02 | E17 | Feeling cloud and smart nudges | Feeling inference: tap plus one follow-up read against medicines, readings and this week's changes; outcomes logged, watched, added to questions, or escalated | System | T1 | P1 | L | E17-01,E04-01 | Red flags open not-feeling-well and notify the roster within one minute; every inference names its reason | Backlog
E17-03 | E17 | Feeling cloud and smart nudges | Smart nudge engine: presence, commitment, pattern, check-in, recognition, anticipation, curiosity, context; two a day; quiet hours; none on alert days | System | T1 | P1 | L | E00-04,E05-06 | Cap enforced per profile per day; every nudge carries why; dismissals feed ranking | Backlog
E17-04 | E17 | Feeling cloud and smart nudges | The number that only goes up on Me | Patient | T1 | P2 | S | E04-02 | Never decreases; no streak language | Backlog
E17-05 | E17 | Feeling cloud and smart nudges | Nudge and check-in metrics: taps per week, Fine-today share, acceptance by kind | System | T1 | P2 | S | E17-03 | Dashboard shows weekly counts per profile | Backlog
E18-01 | E18 | Read-only connectors | Photos on-device scan for documents, boxes and portal screenshots with grid confirmation | Patient | T1 | P1 | M | E00-02 | Nothing uploaded before confirmation; scan of two years completes under a minute | Backlog
E18-02 | E18 | Read-only connectors | Calendar read-only connector: events matching providers or health keywords become candidate appointments | Caregiver | T1 | P1 | S | E03-03 | Candidates suggested, never auto-added | Backlog
E18-03 | E18 | Read-only connectors | Email connector with sender allowlists (Outlook, IMAP first; Gmail after verification); attachments first; review card per item | Caregiver | T2 | P1 | L | E00-02,E02-07 | Only approved senders fetched; each item shown before storage; revocable in one tap | Backlog
E18-04 | E18 | Read-only connectors | WhatsApp family health group ingestion where the platform supports it; forwarding fallback | Everyone | T2 | P1 | M | E19-02 | Non-health messages dropped before storage; ignore honoured | Backlog
E18-05 | E18 | Read-only connectors | Android SMS from allowlisted clinic numbers | Patient | T3 | P3 | S | E00-02 | Reminders and result-ready messages become events | Backlog
E18-06 | E18 | Read-only connectors | Chat export import as a biography source with third-party filtering | Caregiver | T3 | P3 | M | E18-04 | Only messages carrying documents or health events about the owner are kept | Backlog
E18-07 | E18 | Read-only connectors | Connector rules enforcement and audit: purpose-bound, allowlisted, shown before stored, nothing trains anything | System | T2 | P1 | M | E16-05 | Every connector ingestion has an audit entry visible to the owner | Backlog
E19-01 | E19 | WhatsApp agent | Business number, provider, verification and the six approved templates (morning card, visit card, reorder, nudge, digest, red flag) | System | T1 | P1 | M |  | Templates approved; number live in the launch country | Backlog
E19-02 | E19 | WhatsApp agent | Private threads: phone number resolves to Person and keys; free-form replies within the 24-hour window; scope enforced | Everyone | T1 | P1 | L | E00-01,E12-01 | A caregiver asking outside scope gets the same refusal as in the app | Backlog
E19-03 | E19 | WhatsApp agent | Patient Level 0 on WhatsApp: morning card, feeling words, visit card, family notes, OK and button replies | Patient | T1 | P1 | L | E19-02,E11-01 | A patient completes a full day without the app | Backlog
E19-04 | E19 | WhatsApp agent | Group classifier: document, health event, coordination, other; only the first two kept; events become proposals confirmed by the poster | System | T2 | P1 | L | E19-02 | Confirmation tap required before the record changes; receipts file through the review card | Backlog
E19-05 | E19 | WhatsApp agent | Red flags posted by anyone escalate in-thread and to the roster | System | T1 | P1 | S | E11-06 | Escalation within one minute with the panel hospital named | Backlog
E19-06 | E19 | WhatsApp agent | Weekly digest on request and the Sunday recap in the group | Everyone | T2 | P2 | S | E11-09 | Digest covers only kept items | Backlog
E20-01 | E20 | Appointment planner | Appointment planner: read everything since a visit was booked; recommend bring forward, add, sequence, consolidate with rule, evidence, consequence | Caregiver | T2 | P1 | L | E03-01,E00-04,E04-01 | Every recommendation names its rule and evidence; nothing booked without confirm | Backlog
E20-02 | E20 | Appointment planner | Monitoring rules: medicine changes set their own checks; conditions carry cadences; results before reviews | System | T2 | P1 | M | E20-01 | A diuretic change creates a two-week electrolyte check in the plan | Backlog
E20-03 | E20 | Appointment planner | Feelings adjust urgency; red flags bypass the plan to the same-day path | System | T2 | P1 | M | E17-02,E20-01 | Sudden blurring never enters the planner | Backlog
E20-04 | E20 | Appointment planner | Patient one-line plan card with OK | Patient | T2 | P2 | S | E20-01 | One card, plain words, one button | Backlog
E21-01 | E21 | Vertical feed | Vertical full-screen pager: paging scroll, container-relative cards, prefetch, cursor pagination | Patient | T1 | P1 | L | E11-02 | Cards snap one per screen; next page loads within two cards of the end | Backlog
E21-02 | E21 | Vertical feed | Supply order: Now, today's cards, gate, his story, learning; caregiver mode without gate | System | T1 | P1 | M | E21-01 | Gate appears after today's cards; story and learning are endless and profile-scoped | Backlog
E21-03 | E21 | Vertical feed | Card playback: voice on tap, clips with captions, AVQueuePlayer warm-up, never autoplay the next card | Patient | T1 | P1 | M | E21-01 | No card starts audio by itself | Backlog
E21-04 | E21 | Vertical feed | Side actions on every card: Hear, Ask, Family, Not for me | Patient | T1 | P1 | S | E21-01 | Not for me suppresses the card kind for the profile | Backlog
E21-05 | E21 | Vertical feed | Story cards from the record: what the doctor said, number changes, family photos, the proud number | System | T1 | P1 | M | E03-05,E12-02 | Story supply regenerates weekly from memory | Backlog
E21-06 | E21 | Vertical feed | Evergreen learning supply from allowlisted sources per condition and medicine, plain words, in language | System | T1 | P1 | M | E11-04,E16-01 | No card from outside the allowlist; every card cites its page | Backlog
E22-01 | E22 | Plain words and voice | Plain-words verifier in the content service: sentence completeness, readability, glossary, banned words, day-and-date, who-does-next | System | T1 | P1 | M |  | Every patient string fails or passes with a reason; failures cannot ship | Backlog
E22-02 | E22 | Plain words and voice | Glossary and translation memory for English, Malay, Mandarin; the same words every time | System | T1 | P1 | M | E22-01 | Term consistency enforced across cards, voice and WhatsApp | Backlog
E22-03 | E22 | Plain words and voice | Voice scripts: every card rendered as a spoken script with pauses; pre-rendered audio per language; synthesiser fallback | System | T1 | P1 | M | E22-02 | Every patient card has audio within a minute of creation | Backlog
E22-04 | E22 | Plain words and voice | Pharmacist review queue for new sources and the first fifty strings per card type | System | T1 | P1 | S | E22-01 | Nothing from a new source reaches a patient before review | Backlog

## Epics
Epic | Epic name | Stories | T1 | T2 | T3 | P1 | Large
E00 | Platform and data foundation | 9 | 8 | 1 | 0 | 8 | 3
E01 | Onboarding and health biography | 4 | 4 | 0 | 0 | 3 | 1
E02 | Capture and ingestion | 11 | 8 | 3 | 0 | 7 | 4
E03 | Memory and timeline | 7 | 5 | 2 | 0 | 5 | 1
E04 | Medications | 16 | 7 | 8 | 1 | 8 | 1
E05 | Visit loop | 10 | 6 | 4 | 0 | 8 | 1
E06 | Discharge and transitions | 5 | 0 | 4 | 1 | 3 | 2
E07 | Insurance, cost and admin | 6 | 0 | 5 | 1 | 3 | 1
E08 | Care navigation | 5 | 0 | 0 | 5 | 2 | 1
E09 | Intelligence and correlation | 7 | 1 | 5 | 1 | 3 | 3
E10 | Daily living and routines | 4 | 1 | 1 | 2 | 1 | 1
E11 | Delivery, feed and WhatsApp | 10 | 8 | 1 | 1 | 7 | 3
E12 | Family, sharing and helper | 9 | 6 | 1 | 2 | 5 | 1
E13 | Safety and emergency | 4 | 2 | 0 | 2 | 2 | 1
E14 | Symptoms and observations | 3 | 1 | 1 | 1 | 1 | 0
E15 | Design system and accessibility | 7 | 6 | 1 | 0 | 5 | 0
E16 | Trust, boundary and regulatory | 5 | 5 | 0 | 0 | 5 | 0
E17 | Feeling cloud and smart nudges | 5 | 5 | 0 | 0 | 3 | 2
E18 | Read-only connectors | 7 | 2 | 3 | 2 | 5 | 1
E19 | WhatsApp agent | 6 | 4 | 2 | 0 | 5 | 3
E20 | Appointment planner | 4 | 0 | 4 | 0 | 3 | 1
E21 | Vertical feed | 6 | 6 | 0 | 0 | 6 | 1
E22 | Plain words and voice | 4 | 4 | 0 | 0 | 4 | 0
Total |  | 154 | 89 | 46 | 19 | 102 | 32

## Legend
Column | Meaning
ID | Epic code plus a running number. Stable once assigned.
Persona | Dad = patient surface. Chief = adult-child caregiver. Helper = domestic helper on WhatsApp. Clinic = doctor-facing output. All = more than one. System = backend or platform.
Tier | T1 = weeks 0-12, the daily loop. T2 = weeks 12-24, the clinical loop. T3 = weeks 24-36, navigation and media. All three are Stage 1.
Priority | P1 must ship in its tier. P2 should ship in its tier. P3 can slip a tier.
Size | S under a week for a pair. M one to two weeks. L three weeks or more, split before building.
Depends on | IDs that must be done first. Empty means none.
Acceptance criteria | The one test that says the story is done. Expand into scenarios when picked up.
Status, Owner | Fill these in. Status values: Backlog, Ready, In progress, Review, Done.
Source | Stories consolidate stage1-product-design.md, medications-module.md and design-system.md. Sizes and priorities are the author's estimates and should be re-pointed by the team.